## Infra_Information
Sr.No | Component
1 | Vcenter
2 | Esxi
3 | NSX-T
4 | AVI
5 | Tanzu

## Changes-In-Enviornment
Sr.No | Component | Changes/Resolved Issues
1 | Vcenter | vCenter Server 7.0 Update 3j fixes an issue with the export of Inventory objects such as VMs, Hosts and Datastores in the vSphere Client
2 | Esxi | ESXi 7.0 Update 3i supports vSphere Quick Boot on the following server:HPE ProLiant MicroServer Gen10 Plus v2 This release resolves CVE-2022-31696, and CVE-2022-31699.
3 | NSX-T | Provides a new features to offer new functionnalities and enhacement for virtualized networking and security for clouds.
4 | AVI | Network objects in NSX advanced load balancer now sync with the name of the associate port group in Vcenter.
5 | Tanzu | The Tanzu CLI telemetry plugin replaces tanzu mc ceip-participation commands with tanzu telemetry commands. kapp-controller generates ctrl-change ConfigMap objects, even if there is no change Host network pods and node use the wrong IP in IPv6 clusters. When AVI_LABELS is set, ako-operator causes high latency on the AVI Controller With NSX ALB, cannot create cluster in NAMESPACE that has name beginning with numeric character

## Pre-Installation-Tasks
Sr.No | Component | Pre-Installation Tasks
1 | Vcenter | Vcenter vm backup. Check alerts and alarms in vcenter. Check all hosts are healthy. Taken file backup of vcenter on bootstrap server.
2 | Esxi | Host Conifiguration backup. Check alerts and alarms in Exsi Check all hosts are healthy.
3 | NSX-T | NSX-T backup Review the known upgrade problems and workaround documented in the NSX-T Data Center release notes. Check alerts and alarms in NSX-T Verify that the NSX-T Data Center environment is in a healthy state. Check all edge node and transport nodes are reachable from NSX-T Download the latest NSX-T Data Center upgrade bundle.
4 | AVI | AVI backup Check alerts and alarms in AVI Check all Service Engines are healthy. Download the AVI upgrade bundle.
5 | Tanzu | Workload and shared service cluster backup taken through velero on MinIO Take all cluster configuration (configmap,services,deployment,ingress )backup Download the TKG1.6.0 upgrade bundle. Download Tanzu cli ,kubectl and carvel tools.

## Tanzu_Upgrade_Steps
No | Steps | command
1 | TKR OVA template downaload
2 | kubectl and tanzu cli package download
3 | Move downloaded package from Internet PC to Desktop
4 | Docker Image sync in DMZ from vmware repository(replication)
5 | Docker images sync from DMZ to MZ harbor(replication)
6 | TKR OVA template push to vcenter template TKG folder
7 | Delete the ~/.config/tanzu/tkg/compatibility/tkg-compatibility.yaml file.
8 | Create cluster config backup | velero backup create
9 | verify cluster config backup | velero backup list
10 | upgrade tanzu cli package | sudo install core/v0.25.0/tanzu-core-linux_amd64 /usr/local/bin/tanzu
11 | tanzu cli version verify | tanzu version
12 | upgrade kubectl cli package | chmod ugo+x kubectl-linux-v1.23.8+vmware.2 sudo install kubectl-linux-v1.23.8+vmware.2 /usr/local/bin/kubectl
13 | kubectl version verify | kubectl version
14 | upgrade carvel tools ytt , kapp, kbld, imgpkg,vendir | tanzu-cli-bundle-linux-amd64\cli\core\v0.25.0 gunzip ytt-linux-amd64-v0.41.1+vmware.1.gz chmod ugo+x ytt-linux-amd64-v0.41.1+vmware.1 mv ./ytt-linux-amd64-v0.41.1+vmware.1 /usr/local/bin/ytt gunzip kapp-linux-amd64-v0.49.0+vmware.1.gz chmod ugo+x kapp-linux-amd64-v0.49.0+vmware.1 mv ./kapp-linux-amd64-v0.49.0+vmware.1 /usr/local/bin/kapp gunzip kbld-linux-amd64-v0.34.0+vmware.1.gz chmod ugo+x kbld-linux-amd64-v0.34.0+vmware.1 mv ./kbld-linux-amd64-v0.34.0+vmware.1 /usr/local/bin/kbld gunzip imgpkg-linux-amd64-v0.29.0+vmware.1.gz chmod ugo+x imgpkg-linux-amd64-v0.29.0+vmware.1 mv ./imgpkg-linux-amd64-v0.29.0+vmware.1 /usr/local/bin/imgpkg
15 | Tanzu plugins upgrade | tanzu plugins upgrade (plugin name)
16 | Tanzu plugins version verify | tanzu plugins list
| Update tanzu package repository | tanzu package repository update tanzu-standard --url ODCCBSNPHBR.rbi1.rbi.org.in/tkg/packages/standard/repo:v1.6.0 -n tanzu-package-repo-global
17 | Management cluster upgrade | tanzu mc upgrade
18 | tanzu cluster version verify | tanzu cluster list
19 | workload cluster upgrade | tanzu cluster upgrade uat -n uat
20 | tanzu cluster version verify | tanzu cluster list
21 | workload cluster upgrade | tanzu cluster upgrade sit -n sit
22 | tanzu cluster version verify | tanzu cluster list
23 | shared service cluster upgrade | tanzu cluster upgrade sharedservice -n sharedservice
24 | Check for pods running health | kubectl get po -A
25 | check for application accessibility
Note on D18: Ekuber, Ritesh K:

## Venter -Exsi-Upgrade
Vcenter
No | Steps
1 | Download the ISO image for vCenter Server using Internet PC
2 | Transfer Image from internet PC to Desktop using Pen drive
3 | Create backup snapshot of Vcenter VM
4 | Upload Image to vcenter datastore
5 | Make sure that the root password is NOT expired
6 | Mount the ISO and Update with the patch using either VAMI or CLI.
7 | Verify the version upgraded and healthcheck post upgrade
Exsi
No | Steps
1 | Download EXSI patch bundle
Upload Exsi bundle in each host
Put server in maintance mode
Install patch on hosts (esxcli software profile update --depot ESXi-X.X.X-XXXXXXstandard --allow-downgrades --no-sig-check )
reboot the server

## NSX-T Upgrade
No | Steps | command
1 | Upload NSX-T bundle in GUI and perform pre-checks before upgrade .Once all pre-checks are passed do serial upgrade of all component Upgrade your upgrade coordinator Upgrade the NSX Edge cluster. Upgrade the hosts. Upgrade the Management plane. | Perform upgrade from GUI

## AVI Upgrade
No | Steps | command
1 | Upload AVI bundle in GUI and perform pre-checks before upgrade .Once all pre-checks are passed do serial upgrade of all component Upgrade your controller and SE | Perform upgrade from GUI

## Upgrade_Component_Version
Sr.No | Component | Old Version | New Version
1 | Vcenter | 7.0.3.d | 7.0.3.j
2 | Esxi | 7.0.U3si | 7.0.U3si
3 | NSX-T | 3.2.1 | 3.2.2
4 | AVI | 21.1.4 | 22.1.2
5 | Tanzu | TKG1.5.4 | TKG1.6.0

## Update Issues
Component | TKG 1.6.0
Issue | Core addons (antrea, pinniped, metrics-server etc) were failing to reconcile after workload clusters were upgraded from TKG 1.5 to TKG 1.6. Clusters were upgraded to k8s 1.23 version. Customer had 3 workload clusters and management cluster where issue was seen.
Cause | Packages were failing to reconcile since it was not able to fetch the package template images from customer's private registry. This was because the packages were still pointing to projects.registry. vmware.com and not customers registry. Customer didnt use the airgap script to copy images to their registry instead thought just enabling replication in harbor will be enough. But the packages need to be copied using imgpkg tool
Resolution | We used imgpkg to copy the core package repository image as well as kapp-controller image to the customer's airgap registry. We fixed the imageRegistry configuration in tkr-controller-configmap in tkr-system in management cluster to the correct image registry. After this the packages in the management cluster and workload cluster started reconciling fine.

## Post-Installation-Steps
Sr.No | Component | Post-Installation Tasks
1 | Vcenter | Check new version is reflected in vcenter Check alerts and alarms in vcenter. Check all hosts are healthy. Check GUI is accessible.
2 | Esxi | Checl all hosts are accessbile and working fine. Check alerts and alarms in Exsi Check all hosts are healthy.
3 | NSX-T | Check new version is reflected in NSX-T Check GUI is accessible. Check alerts and alarms in NSX-T Check all hosts,edge,transport nodes are healthy. Check all edge node and transport nodes are reachable from NSX-T
4 | AVI | Check new version is reflected in AVI Check GUI is accessible. Check alerts and alarms in AVI Check all Service Engines are healthy.
5 | Tanzu | Check all clusters (management,workload,shared service) are running fine Check new version of TKG Check events in each cluster Check all pods including application and system are running fine. Check all application URL's are accessbile.